● AI SSWB · CONTROL · INSTRUCTOR SOLUTION

Sample output: ED door-to-doctor response plan

A representative AI-drafted response plan from Priya's plain-language description, in control-plan format: a one-line purpose, the response plan table, and the blank response log.

Purpose

Keep ED door-to-doctor time stable, and make sure no chart signal ever goes unanswered. The lead charge nurse reviews the control chart of average daily door-to-doctor time every morning; this plan defines what counts as a signal and exactly what happens next.

Response plan

Each row is one alarm, and each column answers one question the nurse would otherwise have to ask someone. A note on noise: do not overreact to a single point that is still inside the limits. That is ordinary common-cause variation, and the correct response is to leave it alone.

Response plan table

| Signal | First Check | Who to Notify | Corrective Action | What to Record |
| --- | --- | --- | --- | --- |
| Any single point outside the control limits, above the upper or below the lower limit. | Is the admitted-patient room request procedure being followed? Decision-to-admit time recorded, unit contacted promptly, thirty-minute follow-ups, two-hour delays escalated, open requests handed off at shift change. | ED operations manager, same day. | Fix what the first check uncovers: coach on the procedure, escalate stuck room requests, or work the cause with the operations manager. | Date, signal type, cause found, action taken, who responded. |
| Eight points in a row on the same side of the center line. | Same first check. If the procedure is being followed, widen to staffing levels, patient volume, triage delays, bed availability, and physician coverage. | ED operations manager, same day. | Agree the corrective action with the operations manager; keep reviewing the chart daily until the run ends. | Date, signal type, cause found, action taken, confirmation the chart settled. |

Response log

Empty rows waiting for the first entry. The table tells you what to do; the log proves you did it.

Response log table

| Date | Signal | Cause found | Action taken | By | Chart back to normal (date) |
| --- | --- | --- | --- | --- | --- |

What AI supplied, and what Priya must

AI turned a vague good intention, someone really should keep an eye on this, into a concrete, assigned, scannable system in about a minute: the purpose line, the table with one row per signal, the named first check, even the reminder not to overreact to noise. What it could not supply: who actually holds these roles, whether the lead charge nurse has time for a daily check, and whether the night shift needs its own owner. Priya adds real names, real authority, and a checking schedule the team can realistically keep.

The instructor's point

A monitoring tool without a response plan is theater: control is the human action the chart triggers, not the chart itself. And a response plan lives as a table because the person using it is a charge nurse at seven in the morning, not someone sitting down with a manual. That precision, one named owner, a clear escalation contact, a clear alarm definition, and a row the nurse can scan in ten seconds, is what keeps a hard-won improvement from quietly slipping away. AI builds the table in seconds; Priya makes it real.